## Sheet1
	Acceptable, little to no effect	Tolerable, not critical	Unacceptable, affects production heavily	Intolerable, failure in development
Improbable (unlikely to occur)	Issues with net, causing research to slow down and can affect acceptance testing	Deadline can change, thus speeding up development, highly unlikely	Restarting development	Deadline failure	No testing, deploying without testing
Improbable (unlikely to occur)	Issues with the mongodb due to table names etc, causing minor issues with simple solutions	Aggressive deadline, and poor planning	No version control system when hardware fails	Hardware failure, no backups	Team morale
Improbable (unlikely to occur)	Exceptions/ slowed progress	Client can delay progress due to changing plans	No team communication	No design plan, not following a SDLC	No respect amongst team work
Possible (likely occur)	Mental block due to intensive coding	Errors in code due to application updates, especially in git pull	Lack of clarity	Premature optimisation, not paying attention to performance loss	Unfair contribution
Possible (likely occur)	Accidental file or code deletion	Front end not syncing with back-end	Team fatigue	Not committing into a feature branch can replace code and ruin development
Probable (will occur)	MVP priority should be high, no new features till after	Minimal knowledge in backend production, more reused code	Code/Work fatigue	Not being able to meet the mvp/scope creep before mvp is reached
Probable (will occur)	debugging, eliminate bugs	Code issues, slowing development	Dependency issues, different versions etc	Lack of knowledge
Probable (will occur)	Git commit and push issues i.e. pull first, unrelated merge histories.	Expectations in code scalability	Not being able to fix a code bug	Deadline can cause rushed development and deployment

			color code heat (darker = bigger impact)
			0 - 19%
			20-39%
			40-59%
			60-69%
			70-79%
			80% +